{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["2022年上半年项目库调整 "],"not_rendered":{"external_links":1,"defined_names":2},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"2022年上半年项目库调整 ","index":0,"n_rows":57,"n_cols":26,"rows_kept":57,"merged":[[0,0,0,1],[1,0,1,25],[2,0,2,3],[2,4,2,5],[2,7,2,8],[3,0,5,0],[3,1,5,1],[3,2,5,2],[3,3,5,3],[3,4,5,4],[3,5,5,5],[3,6,5,6],[3,7,5,7],[3,8,3,9],[3,10,5,10],[3,11,5,11],[3,12,3,18],[3,19,3,24],[3,25,5,25],[4,8,5,8],[4,9,5,9],[4,12,5,12],[4,13,4,14],[4,15,4,16],[4,17,4,18],[4,19,5,19],[4,20,5,20],[4,21,4,22],[4,23,4,24],[52,0,52,2],[52,4,52,5],[53,0,53,2],[53,4,53,5],[54,0,54,2],[54,4,54,5],[55,0,55,2],[55,4,55,5],[56,0,56,2],[56,4,56,5]],"flags":["formulas_cached_only"]}
["附件:8"]
["抚远市2022年巩固拓展脱贫攻坚成果和乡村振兴项目库基本情况表"]
["填报单位：",{"$nulls":3},"联系人：",null,null,"联系电话："]
["序号","项目库年度","项目名称","项目类别","内容类型","实施地点","建设性质","建设任务","工期进度",null,"责任单位","项目归口单位","资金规模及来源（万元）",{"$nulls":6},"带贫减贫机制",{"$nulls":5},"绩效目标"]
[{"$nulls":8},"开工时间","竣工时间",null,null,"小计","财政专项扶贫资金",null,"整合资金",null,"其他资金",null,"方式","群众参与","受益对象",null,"收益情况"]
[{"$nulls":13},"中央、省资金","市、县资金","整合类别","资金额度","贷款","自筹",null,null,"贫困户","非贫困户","总收益","贫困户总收益"]
[1,2022,"购置农机具项目","产业项目","产业扶贫","民富村","新建","购置2604拖拉机1台及配套农机具",2022.6,2022.11,"别拉洪乡政府","农业农村局",86,86,{"$nulls":8},125,null,null,"购买农机车≧1台、套；项目(工程)完成及时率≧100%；补助标准86万元/台、套，受益人口户数≧125户；工程使用年限≧10年"]
[2,2022,"购置农机具项目","产业项目","产业扶贫","东岗村","新建","购置割晒机2台",2022.3,2022.12,"寒葱沟镇政府","农业农村局",30,30,{"$nulls":7},8,248,null,null,"购置割晒机≥2台，每台补助≥15万元，带动脱贫户≥8户，增加脱贫户和村集体收入。"]
[3,2022,"购置农机具项目","产业项目","产业扶贫","双胜村","新建","购置割晒机2台",2022.5,2022.12,"浓江乡政府","农业农村局",30,30,{"$nulls":8},"258户（580人）",null,null,"购置割晒机≧2台；当年开工率≧100%、当年完成率≧100%；受益贫困人口数≧4户；工程使用年限≧10年"]
[4,2022,"购置农机具项目","产业项目","产业扶贫","东红村","新建","购买1台收割机、1台农用四轮车及配套设备",2022.7,2022.12,"通江镇政府","农业农村局",107,107,{"$nulls":7},7,321,null,null,"购买收割机≧1台、套；购买农用四轮车及配套设备≧1台、套项目(工程)完成及时率≧100%；收割机补助标准75万元/台、套，农用四轮车及配套设补助标准32万元/台、套，受益人口户数≧7户；工程使用年限≧10年"]
[5,2022,"光伏电站项目","产业项目","产业扶贫","海源村","新建","新建村级光伏电站200kw3000㎡",2022.5,2022.12,"海青镇政府","发改局",120,120,{"$nulls":7},2,42,null,null,"建设光伏发电站≧1个；当年开工率≧100%、当年完成率≧100%；受益贫困人口数≧5人；补助标准≧120万；工程使用年限≧10年"]
[6,2022,"光伏电站项目","产业项目","产业扶贫","红旗村","新建","新建光伏发电站300kwp，占地面积9000平方米",2022.03,2022.12,"寒葱沟镇政府","发改局",220,220,{"$nulls":7},14,557,null,null,"新建村级光伏电站，建设总规模≧300千瓦、当年开工率≧100%、当年完成率≧100%、受益贫困人口数≧5户；光伏扶贫电站持线运营年限≧20年。"]
[7,2022,"光伏电站项目","产业项目","产业扶贫","新兴村","新建","新建光伏发电站200kwp，占地面积5000平方米",2022.3,2022.12,"寒葱沟镇政府","发改局",150,150,{"$nulls":7},5,227,null,null,"新建村级光伏电站，建设总规模≧200千瓦、当年开工率≧100%、当年完成率≧100%、受益贫困人口数≧5户；光伏扶贫电站持线运营年限≧20年。"]
[8,2022,"光伏电站项目","产业项目","产业扶贫","良种场","新建","新建光伏发电站300kwp，占地面积18000平方米",2022.03,2022.12,"寒葱沟镇政府","发改局",220,220,{"$nulls":7},4,85,null,null,"新建村级光伏电站，建设总规模≧200千瓦、当年开工率≧100%、当年完成率≧100%、受益贫困人口数≧2户；光伏扶贫电站持线运营年限≧20年。"]
[9,2022,"光伏电站项目","产业项目","产业扶贫","南岗赫哲族村","新建","建设光伏电站规模400千瓦，占地面积1.2万平方米",2022.5,2022.12,"黑瞎子岛镇政府","发改局",280,280,{"$nulls":7},1,152,null,null,"新建设光伏≥400千瓦；占地面积≥1.2万平方米；当年开工率≥100%；项目完工率≥100%；补助标准≥280万元；工程使用年限≥10年，预计年收益12万元。"]
[10,2022,"光伏电站项目","产业项目","产业扶贫","浓江村","新建","新建村级光伏电站300kwp,10000㎡",2022.5,2022.12,"浓江乡政府","发改局",220,220,{"$nulls":7},"6户（10人）","239户（527人）",null,null,"村级光伏电站建设总规模≧300千瓦、当年开工率≧100%、当年完成率≧100%、受益贫困人口数≧66人；光伏扶贫电站持线运营年限≧20年。"]
[11,2022,"光伏电站项目","产业项目","产业扶贫","建胜村","新建","新建光伏电站200KW，占地5000平方米。",2022.09,2022.12,"浓桥镇政府","发改局",140,140,{"$nulls":7},19,272,null,null,"新建光伏发电站≧200千瓦，当年开工率100%，完成度100%；补助标准140万/处；贫困户受益≧2000元/年。受益贫困户≧19户；光伏扶贫电站持线运营年限≧20年。"]
[12,2022,"光伏电站项目","产业项目","产业扶贫","长征村","新建","新建光伏电站150KW，占地4000平方米。",2022.09,2022.12,"浓桥镇政府","发改局",110,110,{"$nulls":7},5,150,null,null,"新建光伏发电站≧150千瓦，当年开工率100%，完成度100%；补助标准110万/处；贫困户受益≧2000元/年。受益贫困户≧5户；光伏扶贫电站持线运营年限≧20年。"]
[13,2022,"光伏电站项目","产业项目","产业扶贫","东方红村","新建","新建光伏电站200KW，占地4000平方米。",2022.09,2022.12,"浓桥镇政府","发改局",120,120,{"$nulls":7},33,799,null,null,"新建光伏发电站≧200千瓦，当年开工率100%，完成度100%；补助标准120万/处；贫困户受益≧2000元/年。受益贫困户≧6户；光伏扶贫电站持线运营年限≧20年。"]
[14,2022,"光伏电站项目","产业项目","产业扶贫","镇西村","新建","新建400千瓦光伏电站一座，占地面积12000平米",2022.01,2022.12,"鸭南乡政府","发改局",240,240,{"$nulls":7},2,162,null,null,"光伏电站一座，补助标准240万/座；受益贫困人口数≧2人；使用年限≧20年"]
[15,2022,"光伏电站项目","产业项目","产业扶贫","永丰村","新建","新建光伏电站规模200千瓦，占地面积3000平方",2022.6,2022.12,"乌苏镇政府","发改局",140,140,{"$nulls":7},3,148,null,null,"新建光伏电站≥200千瓦；占地面积≥3000平方米；当年开工率≥100%；项目完工率≥100%；补助标准≥140万元；工程使用年限≥20年。"]
[16,2022,"双胜村1期光伏电站","产业项目","产业扶贫","双胜村","新建","新建村级光伏电站300kwp,10000㎡",2022.5,2022.12,"浓江乡政府","发改局",220,220,{"$nulls":8},"258户（580人）",null,null,"村级光伏电站建设总规模≧300千瓦、当年开工率≧100%、当年完成率≧100%、受益贫困人口数≧66人；光伏扶贫电站持线运营年限≧20年。"]
[17,2022,"村内道路硬化","基础设施","基础设施建设","永发村","新建","新建3公里长，4米宽，厚0.2米，水泥硬化及路肩回填。",2022.5,2022.12,"海青镇政府","农业农村局",270,270,{"$nulls":7},1,254,null,null,"村内道路硬化≧3公里；当年开工率≧100%、当年完成率≧100%；受益贫困人口数≧3人；补助标准≧90万元/每公里；工程使用年限≧10年"]
[18,2022,"村内道路硬化","基础设施","基础设施建设","海宏村","新建","拆除原始破损路面，新建0.43公里长，4米宽，厚0.2米，水泥硬化及下涵管4处24米。",2022.05,2022.12,"海青镇政府","农业农村局",45,45,{"$nulls":7},20,388,null,null,"村内道路硬化≧0.43公里；当年开工率≧100%、当年完成率≧100%；受益贫困人口数≧39人；补助标准≧262元/平方米；工程使用年限≧10年"]
[19,2022,"村内道路硬化","基础设施","基础设施建设","建兴村","新建","村内道路硬化1.4公里，3.5米宽",2022.6,2022.11,"浓桥镇政府","农业农村局",110,110,{"$nulls":7},6,118,null,null,"新建水泥路≧1.4公里；当年开工率≧100%、当年完成率≧100%；受益贫困人口数≧6人；补助标准≧77万/公里；工程使用年限≧10年"]
[20,2022,"地秤","基础设施","基础设施建设","永胜村","新建","新建一处150吨地秤，40平米看护房，硬化路面15米宽3.5米",2022.6,2022.12,"乌苏镇政府","农业农村局",30,30,{"$nulls":7},2,92,null,null,"新建地秤≥150吨；带动增加贫人口收入≧500元每户/年；受益贫困人口户数≧2户；使用年限≥10年，当年开工率≧100%"]
[21,2022,"涵管","基础设施","基础设施建设","红丰村","新建","规格1X2米涵管80节",2022.1,2022.12,"寒葱沟镇政府","农业农村局",6.4,6.4,{"$nulls":7},10,188,null,null,"铺设涵管≥80节，补助资金800元/节。当年开工率≧100%、当年完成率≧100%。完成后改善农田水利和农田路畅通。"]
[22,2022,"涵管","基础设施","基础设施建设","红卫村","新建","铺设涵管20节×DN800",2022.05,2022.12,"寒葱沟镇政府","农业农村局",1,1,{"$nulls":7},2,273,null,null,"铺设涵管≥20节，补助资金≥500/节， 当年开工率≥100%，当年完成率≥100%，完成后改善村民增产增收。"]
[23,2022,"涵管","基础设施","基础设施建设","东发村","新建","规格1X2米涵管40节",2022.7,2022.12,"通江镇政府","农业农村局",2.4,2.4,{"$nulls":7},1,109,null,null,"桥涵具备良好通行条件，方便种地户作业，提高农业生产效率。群众满意度≥100％当年开工率≧100%、当年完成率≧100%。完成后改善农田水利和农田路畅通。工程使用年限≧10年"]
[24,2022,"涵管","基础设施","基础设施建设","八盖村","新建","涵管(60cm)140节",2022.6,2022.12,"乌苏镇政府","农业农村局",10,10,{"$nulls":7},14,162,null,null,"涵管≥140节；受益贫困人口户数≧14户；受益户数≥176户；；开工率≥100%；完工率≥100%；验收率≥100%；使用年限≥5年"]
[25,2022,"涵管","基础设施","基础设施建设","别拉洪村","新建","涵管20节（80CM）",2022.6,2022.12,"乌苏镇政府","农业农村局",2,2,{"$nulls":7},1,35,null,null,"购买涵管≥20节；受益户数≥36户；开工率≥100%；完工率≥100%；验收率≥100%；使用年限≥5年"]
[26,2022,"涵管","基础设施","基础设施建设","东胜村","新建","涵管80节（60CM）",2022.6,2022.12,"乌苏镇政府","农业农村局",4.8,4.8,{"$nulls":7},5,113,null,null,"购买涵管≥80节；受益户数≥118户；开工率≥100%；完工率≥100%；验收率≥100%；使用年限≥5年"]
[27,2022,"路边沟","基础设施","基础设施建设","海青村","新建","新建路边沟8公里。",2022.5,2022.12,"农场事务中心","农业农村局",360,360,{"$nulls":7},6,398,null,null,"新建路边沟≧8000延长米；当年开工率≧100%、当年完成率≧100%；补助标准450元/米；受益脱贫人口数≧9人；工程使用年限≧5年"]
[28,2022,"农机停放库","基础设施","基础设施建设","东安村","新建","新建库房1200㎡，及配套设施",2022.5,2022.12,"黑瞎子岛镇政府","农业农村局",140,140,{"$nulls":7},1,152,null,null,"新建停放库≥1200㎡；场地硬化≥1200㎡；当年开工率≥100%；项目完工率≥100%；补助标准≥1166元/㎡；工程使用年限≥10年。"]
[29,2022,"农田路","基础设施","基础设施建设","海兴村","新建","3公里长，4米宽，厚0.2米，下涵管12节，24延长米。",2022.03,2022.12,"海青镇政府","农业农村局",60,60,{"$nulls":7},7,297,null,null,"村内道路硬化≧3公里；当年开工率≧100%、当年完成率≧100%；受益贫困人口数≧10人；补助标准≧20万/公里；工程使用年限≧10年"]
[30,2022,"农田路","基础设施","基础设施建设","红卫村","新建","农田路铺砂石3公里，宽4米，厚0.3米",2022.05,2022.12,"寒葱沟镇政府","农业农村局",48,48,{"$nulls":7},2,273,null,null,"铺设砂石≥3000米，当年开工率≥100%，当年完成率≥100%，道路补助16万/公里，使用年限≥5年，受益农户≥273户，受益脱贫户≥2户，完成后改善村民增产增收。"]
[31,2022,"农田路","基础设施","基础设施建设","红星村","新建","修建砂石路2.5公里，宽4米厚0.3米",2022.03,2022.12,"寒葱沟镇政府","农业农村局",40,40,{"$nulls":8},8,null,null,"铺设砂石农田路≥2.4千米，当年开工率≧100%、当年完成率≧100%。道路补助16万元/公里，使用年限≧5年，受益农户≧6户，完成后改善900亩耕地的农田路通畅"]
[32,2022,"农田路","基础设施","基础设施建设","双胜村","新建","新建农田路4.5公里，宽4米，厚0.3米，石料5400m³",2022.5,2022.12,"浓江乡政府","农业农村局",90,90,{"$nulls":8},"258户（580人）",null,null,"续建农田路≧4.5公里；当年开工率≧100%、当年完成率≧100%；受益人口数≧568人；工程使用年限≧10年"]
[33,2022,"农田路","基础设施","基础设施建设","生德库村","新建","新建农田路5公里，宽4米，厚0.3米，",2022.5,2022.12,"浓江乡政府","农业农村局",100,100,{"$nulls":8},"332户（728人）",null,null,"续建农田路≧5公里；当年开工率≧100%、当年完成率≧100%；受益人口数≧728人；工程使用年限≧10年"]
[34,2022,"农田路","基础设施","基础设施建设","建设村","新建","维修农田砂石路6公里、宽3.5米、厚0.3米；需毛石420车，每车15方。",2022.08,2022.12,"浓桥镇政府","农业农村局",70,70,{"$nulls":7},7,150,null,null,"铺设砂石≥6公里，当年开工率≧100%、当年完成率≧100%。道路补助14万元/公里，使用年限≧5年，受益农户≧157户，受益脱贫户≧7户；工程使用年限≧10年"]
[35,2022,"农田路","基础设施","基础设施建设","建兴村","新建","新建农田砂石路5公里、宽3.5米、厚0.3米；",2022.08,2022.12,"浓桥镇政府","农业农村局",60,60,{"$nulls":7},6,118,null,null,"铺设砂石≥5公里，当年开工率≧100%、当年完成率≧100%。道路补助14万元/公里，使用年限≧5年，受益农户≧118户，受益脱贫户≧6户；工程使用年限≧10年"]
[36,2022,"农田路","基础设施","基础设施建设","八盖村","新建","新建砂石路长5.7公里，宽3.5米，厚度30公分",2022.6,2022.12,"乌苏镇政府","农业农村局",70,70,{"$nulls":7},14,162,null,null,"新建农田路≥5700延长米；宽度≥3.5米；厚度≥0.3米；受益贫困人口户数≧14户；受益户数≥176户；开工率≥100%；完工率≥100%；验收率≥100%；使用年限≥10年"]
[37,2022,"农田路","基础设施","基础设施建设","永胜村","新建","新建砂石路长1公里，宽3.5米，厚度30公分",2022.6,2022.12,"乌苏镇政府","农业农村局",12,12,{"$nulls":7},2,92,null,null,"新建农田路≥1000延长米；宽度≥3.5米；厚度≥0.3米；受益贫困人口户数≧2户；受益户数≥92户；开工率≥100%；完工率≥100%；验收率≥100%；使用年限≥10年"]
[38,2022,"农田路","基础设施","基础设施建设","北岗村","新建","新建砂石路3000米.宽3.5米，厚25公分",2022.6,2022.12,"乌苏镇政府","农业农村局",40,40,{"$nulls":7},4,238,null,null,"新建农田路≥3000米；受益户数≥238户；开工率≥100%；完工率≥100%；验收率≥100%；使用年限≥10年"]
[39,2022,"桥涵","基础设施","基础设施建设","红丰村","新建","新建2X2X10米盖板桥一座",2022.1,2022.12,"寒葱沟镇政府","农业农村局",14,14,{"$nulls":7},10,188,null,null,"修建盖板桥数量≧1座；补助标准每座桥≧14万元；受益人口户数≧198户；工程使用年限≧10年"]
[40,2022,"清理沟渠","基础设施","基础设施建设","新兴村","新建","农田路排水沟清淤30公里",2022.1,2022.12,"寒葱沟镇政府","农业农村局",9,9,{"$nulls":7},5,227,null,null,"村内路边沟清淤≥30公里，当年开工率≧100%、当年完成率≧100%。道路补助0.3万元/公里，使用年限≧5年，受益农户≧228户，受益贫困户≧5户，完成后改善村民居住环境"]
[41,2022,"清理沟渠","基础设施","基础设施建设","双胜村","新建","疏通涵洞10个，疏通沟渠4公里",2022.5,2022.12,"浓江乡政府","农业农村局",15,15,{"$nulls":8},"258户（580人）",null,null,"当年开工率≧100%、当年完成率≧100%；受益贫困人口数≧4户；工程使用年限≧10年"]
[42,2022,"自来水改造","饮水安全","饮水安全建设","红卫村","维修","自来水主管道及入户网改造维修5000延长米",2022.05,2022.12,"寒葱沟镇政府","水务局",90,90,{"$nulls":7},2,273,null,null,"改善饮水条件，保障饮水安全，当年开工率≥100%，完工率≥100%，帮扶户受益≥2户。工程使用年限≧10年"]
[43,2022,"雨露计划","雨露计划项目","贫困大学生资助","全市","新建","为全市脱贫户家庭学生提供资助",2022.1,2022.12,"乡村振兴局","乡村振兴局",4,4,{"$nulls":11},"资助贫困户子女人数≧12人；接受补助的学生中建档立卡贫困户子女占比≧100％；资助标准达标率≧100％；资助标准达标率≧100％；资助经费及时发放率≧100％；建档立卡贫困户子女生均资助标准1500元/学年；受益贫困人口数≧20人；建档立卡贫困户子女全程全部接受资助的比例≥100%；受助学生满意度≥100%"]
[44,2022,"项目管理费","其他","其他","全市","新建","项目管理费",2022.1,2022.12,"乡村振兴局","乡村振兴局",230,230,{"$nulls":11},"项目管理费及时发放率≥100%；受益脱贫人口满意度≥100%"]
[45,2022,"脱贫劳动力外出务工交通补贴","其他","脱贫户补贴","全市","新建","为全市脱贫户提供外出务工交通补贴",2022.1,2022.12,"乡村振兴局","乡村振兴局",3,3,{"$nulls":11},"脱贫劳动力外出务工交通补贴人次数≥60人次；脱贫劳动力外出务工交通补贴发放准确率≥100%；脱贫劳动力外出务工交通补贴人均标准≤500元；受益脱贫人口满意度≥100%"]
[{"$nulls":12},4369.6]
["总计",null,null,"45项","4369.6万元"]
["产业项目",null,null,"16项","2433万元"]
["基础设施",null,null,"25项","1609.6万元"]
["饮水安全",null,null,"1项","90万元"]
["其他",null,null,"3项","237万元"]